## Sheet1
ApplicationName | Assignee | ApplicationOwner | ETA | ActualCompletion | Status | Remarks | Instructions :
Offshore Hiring portal | Gokila | Prathima | 2018-12-07 |  | Awaiting Inputs | Adding Financial year dropdown, Changing Quarter to Report Period,Multi Select options for Segment and maintaining past years data Awaiting inputs from Prathima | *All Records must be entered in consecutive rows.
Freshers Portal | Gokila | Prathima | 2018-12-07 |  | Awaiting Inputs | Adding Financial year dropdown, Changing Quarter to Report Period,Regular stream to Stream and have multi seect options for Stream ,Multi Select options for Segment and maintaining past years data Awaiting inputs from Prathima | * Please Select Status from the Dropdown in Status column
Consolidated BE Reprot | Gokila | Sheethal | 2018-02-12 |  | Completed | Refactoring the code for consolidated BE Report | * Date should be YYYY-MM-DD Format (e.g 2019-03-12)
BE Admin Console | Rashmin | SriRam | 2018-12-02 |  | Completed | Issues with BE Admin Console
USDLY and Daily Utilization Mailer | Rashmin | Anish | 2018-07-12 |  | Completed | Mofification of the Automation Employee load script to include USDLY data.
Volume Load Automation | Hitesh | Ravi | 2018-12-05 |  | Completed | Complete automation of Volume Load(Including Reports download, and Loading the data into tables)
BOT | Neelam | Sheethal | 2018-12-31 |  | Completed | Prod Count
BOT | Neelam | Sheethal | 2018-12-07 |  | Completed | Upload Feature, Getting Prod Counts
Visa Dashboard | Neelam | Amit | 2018-12-05 | 2018-12-03 | Completed | Renaming two columns and changing few Values in the Reasons Drop Down
DS BE Tracker | Abinaya | Sendil | 2018-12-01 |  | Completed | To include Q4 Targets and add rows for Q4
Manpower report automation | Abinaya | Ajay,Deepak | 2018-12-07 |  | Completed
Volume Load Automation | Hitesh | SriRam | 2018-12-07 |  | Completed | An excel report which compares the PBS count Vs Alcon Count For the current month and send mailers to SPO team
BUR Consolidated Macro | Rashmin | Sheethal | 2018-12-03 |  | Completed | Automated
USDLY reporting | Rashmin | Sheethal | 2018-12-04 |  | Completed
Merge Accounts in BE tracker | Rashmin | Ravi | 2018-12-04 |  | Completed | Merge Acounts in new BE Tracker
Digital RTBR | Gokila | Deepak | 2018-12-04 |  | Completed | Needs Fix
Volume Load Automation | Hitesh | SriRam | 2018-12-11 |  | Completed | Pivot Sheets based on the volume Data. Practice Wise file generation Automation
Practice View of Digital RTBR-DEvOps | Gokila | Deepak | 2018-12-11 |  | Completed | Pratice View of Digital RTBR report for DevOPs was included in the Report
Visa Dashboard | Neelam | Amit | 2018-12-17 |  | Completed | 1) Stamping Status 2)Already Travelled once 3)Cumulative stay in US ( Months)
Sharepoint Data Upload Automation | Rahul | Sheethal |  |  | Completed | Sharepoint automation in server
RTBR Load Automation | Gokila | Ravi | 2018-12-14 |  | Completed | Downloadable Excel Report of validated RTBR File -- Project Currency, USD Mailer after load is done
RTBR Load Automation | Abinaya | Ravi/Anish | 2018-12-19 |  | Completed | Automation of Downloading RTBR report for upload
Sharepoint upload-- Manpower report Automation | Abinaya | Ajay,Deepak | 2018-12-14 |  | Completed | Manpower Load Package is Fixed. Sharepoint site changed due to which existing automation has failed. Needs to be fixed.
RTBR Load Automation | Gokila | Ravi/Anish | 2018-12-11 |  | Completed | Modifying the report as per the required format and loading the data on to the tables
BE Tracker | Gokila | Deepak | 2019-01-31 |  | Completed | Add IOT ServicelInein BE Tracker
BPO TSO Changes | Gokila, Nandita | Deepak | 2019-01-24 |  | Completed | Updating Actual Values for previous Months
StatusTracker | Nandita | Sheethal | 2019-01-31 |  | Completed | A tracker to add all the Tasks which are in Progress, Completed and Yet to Start
Software Installation | Rashmin | Sheethal | 2019-01-31 |  | Completed | Getting BOT softwares, Visual Studio 2015, SQL Server
BE Tracker | Rashmin, Gokila, Neelam | Sheethal | 2019-01-31 |  | Completed | Code refactoring for downloading Volume BE Sheets
Software Installation | Hitesh | Sheethal | 2019-01-31 |  | Completed | Visual Studio 2010, SQL Server
,, | Teja | Sheethal | 2019-04-12 |  | Completed | Taking backup of all the frozen reports, Applications, Packages and Macros to new server
RTBR Automation | Rahul | Ajay | 2019-02-05 | 2019-02-05 | Completed | Upload Practice wise data for Project Level RTBR 31st March
RTBR Automation | Rahul | Crystal | 2019-02-05 | 2019-02-05 | Completed | Upload Practice wise data after the RTBR load, for validated files
KT From Abinaya | Abinaya | Sheethal | 2019-02-20 |  | Completed | KT On all the applications Abinaya is taking care of
Volume Gaps(Monthly) Vs Release list | Hitesh | Anish |  |  | NOT IN USE | Compare Volume as on Previous Month and Current Date. The difference to be verified in Release list
Including USDLY Buffer and Training Data in the emp Load | HItesh | TPD |  |  | Completed | Adding USDLY training and Buffer Data in Emp Load
Including USDLY IVS IN Buffer and Training Tracker | Nandita, Teja, Rakesh | TPD |  |  | Completed | Adding USDLY In Buffer and Training portal
Migration | Hitesh | Sheethal |  |  | Completed | Migrating SSIS packes to the new VM
RBR Load automation | Gokila | Ravi/Anish | 2018-12-20 |  | Completed | Scheduling the Package
Reprot to compare Volume, Alcon Counts | Rashmin | Sheethal | 2018-12-28 |  | Completed | A report to compare the Volume Numbers and Alcon Numbers with yest Count and send a mailer to dashboard team if the count is Greater or Lesser than 10
Sharepoint Data Upload -- Date needs to be included | Abinaya | Deepak | 2018-12-31 |  | Completed | Add Date to the file before uploading it o sharepoint
RTBR Macro | Rashmin | Sheethal | 2019-01-04 |  | Completed | Handle Exceptions in RTBR
BE Admin console | Neelam | Sheethal | 2019-01-09 |  | Completed | Adding IOT in the bE Admin console Page
BOT Migration | Neelam | Sheethal | 2019-04-19 |  | Completed | Migrating BOT to the New VM
Volume Report | Rahul | Crystal |  |  | NOT IN USE | Volume report to be pivoted and sharepoint upload of data at practice level
Emp Load | Rashmin | Rashmin |  |  | Completed | Manpower Load Refactoring, Including IPS IVS
Be Tracker | Rashmin | Ramkumar Akilen |  |  | Completed | Re-Naming Columns in Volume BE report
Migration | Rashmin, Hitesh, Rakesh | Sheethal |  |  | Completed | Migrating all the applications in the new server for Testing
Report Sever | Sheethal | Sheethal |  |  | Stopped | Setting up Reporting Services in the new VM
Including IOT in SS Total | Gokila | Deepak | 2019-02-15 |  | Completed | Including IOT in SS Totals in all BE Related Reports
Status Tracker | Nandita | Sheethal | 2019-02-20 |  | Completed | A report to show the status of the applications being worke don by the Dashboard Team
Merge Accounts in BE tracker | Rashmin | Ravi | 2018-12-04 |  | Completed | Merge Acounts in new BE Tracker
Volume Gaps Portal | Gokila | Deepak | 2019-02-14 |  | Completed | To include IOTIn Volume BE gaps Report
Adding code to GitHub | Sheethal | Sheethal |  |  | Yet-To-Start
Adding SS DU Group RTBR | Gokila, Rahul | Ajay,Deepak | 2019-02-20 |  | Completed | Adding SS DU Group as a column in RTBR report
ONB USDLY Tracker | Neelam | TPD |  |  | Completed
Cube for Mapower | Nandita | TPD | 2019-02-25 |  | Completed
Report for Buffer USDLY | Rakesh | TPD |  |  | Completed
Including ATA USDLY in Emp Load | Hitesh | Sheethal |  |  | Completed
Digital View of Financial Data | Rakesh, Gokila | Deepak, Anish | 2019-04-19 |  | Completed | Report to display Volume, Revenue , RTBR and commitment values
Consolidated BE Reprot CallDate Issue | Gokila | Ravi |  |  | Completed
ONB Excel Upload | Teja | TPD |  |  | Completed | USDLY ONB Excel Upload
DH BE Tracker | Gokila | Ravi |  |  | Completed | DH BE Tracker, Account level 31st march for Next and Next Qurter
DM Mappings in Report | Nandita | Ravi |  |  | Completed | Having DM names in all the reports of BE tracker
ZD Automation | Rahul | Sheethal |  |  | Completed | Autmation of ZD Application
USDLY ONB Reports | Rakesh | TPD |  |  | Completed | Having ONB report for different Age Brackets
RTBR Cube Changes | Rahul | Ravi | 2019-04-19 |  | Completed | Refactored RTBR Cube code
ATA PM Cube | Teja | Deepak | 2019-03-22 |  | Completed | Having project DU mapping based on Mapped pU
ATA PM Cube | Gokila | Sriram | 2019-04-19 |  | Completed | New columns created for Margin Tracker
ZD-- Self Service Portal | Rahul | Sheethal | 2019-03-29 |  | Completed | A page to add/ Del/Modify
RTBR Validated File | Gokila | Deepak | 2019-03-26 |  | Completed | The Logic for Mapping SSDU Groups to be changed
RTBR Cube Changes | Rahul | SriRam | 2019-04-05 |  | Completed | 31st March Rates to be added to 3 months
Allocation Expiry | Rakesh | Users | 2019-04-10 |  | Completed | Filters and Bulk Upload Not Working
Actuals Split for Fuctional,Non-Functionalion,ss | Gokila | Sheethal | 2019-04-19 |  | Completed | Actuals to be uplaoded at Functional and SS Split
Package Configurations | Rahul | Sheethal |  |  | Yet-To-Start | Make connections general in all the packages
Fixing Issues in Volume Load | Hitesh | Deepak | 2019-04-24 |  | Completed
Fixing RTBR SSDU Group Mapping | Rahul | Deepak | 2019-04-24 |  | Completed
Fixing Volume Gaps Portal SS issues | Rashmin | Deepak | 2019-04-24 |  | Completed
Home Page- Be Portal | Gokila | Srini | 2019-04-25 |  | Completed | Addition of a new column -- Practice. Data to be collapsed at practice level
Week On Week BE Changes | Teja | Srini | 2019-04-26 |  | Completed | Current Call Date - Previous Call Date data, and the gaps, at practice level
Digital View of Financial Data | Rakesh | Sheethal | 2019-05-07 |  | Completed | Making the query Robust by Adding the logic for getting proper RTBR values once the actuals are out.
RTBR Report-- SS Split | Rahul, Gokila | Deepak | 2019-05-10 |  | Completed | Having the SS Split in the RTBR Gaps report just like volume gaps report
BOT Migration | Rakesh, Neelam | Sheethal | 2019-05-10 |  | Completed | Migrating BOT to the latest Version
Portal to add SS Du Groups | Rakesh | Sheethal | 2019-05-03 |  | Completed | A portal to add SS DU group
Freeze Revenue BE in BE Tracker | Gokila | Ravi | 2019-05-13 |  | Completed | Freezing RevenueBE once Actuals are out for a particular Month
OMS Automation | Teja | Deepak | 2019-05-17 |  | Completed | OMS report sent by Deepak to IVS MailAssist to be automated and the OMS Dump to be loaded
Adding SS Others to BE Tracker | Gokila | Ravi |  |  | Completed | SS others to be added to BE tracker
Adding DM Name | Rashmin | Ravi |  |  | Completed | DM name has to be added in Fin Cube
Adding Region | Rahul | Ravi |  |  | NOT IN USE | Adding Region to Revenue Report, Volume Report and Fin Cube
Send Mail to DMs Buffer Portal - USDLy | Rakesh | Pradeep |  |  | NOT IN USE | Sending Automated mailers to the DMs based on some conditions in Buffer Portal
BE Tracker Home Page | Rashmin | Ravi |  |  | Completed | Home page report is now access based. Functional Folks will see data ata Account level and SS Folks will view data at SS Level
DS BE Tracker | Teja | Sendil |  |  | Completed | Enabling DS BE tracker for q2
Volume Gaps Report | Hitesh | Ravi |  |  | Completed | Adding Functional part
RTBR BE Gaps Report | Rahul | Ravi |  |  | Completed | Adding Functional part
Revenue BE Report | Rashmin | Ravi |  |  | Completed | Removing Nulls from revenume columns and adding segment, sub segment details
DS BE Tracker | Teja, Rashmin | Sheethal |  |  | Completed | Refactoring the code, as there are lot of repetations in the code
Modifying Missing DU s list | Teja | Sheethal |  |  | Completed | Add the Count of Missing Dus. A jump report which displayes the emp details
Consolidated Report | Gokila | Ravi | 2019-07-12 |  | Completed | Refactoring the Consolidated BE Report to make it work as a cube
RTBR Load | Rahul | Sheethal | 2019-08-20 |  | Completed | Refactoring the RTBR Load
Allocation Expiry Tracker | Rahul | Sendil |  |  | Completed | Adding 3 column to Allocation Expiry Tracker 1) Adding a non editable field -- Staffing End Date 2) Adding a non Editable Field -- Primary Skills 3) Adding an Editable Column -- Addditional Skills
Bot Deployment | Rakesh | Sheethal | 2019-08-20 |  | NOT IN USE | Deploying BOT to Tomcat, so that it runs as a service
Buffer Portal | Teja | Sendil | 2019-07-22 |  | Completed | Adding Planned Billing Date, Remarks Contraints, SED, Employee Skills
Allocation Expiry TRacker | Himanshu | Sendil |  |  | Completed | Adding a column, Due Date for Cross Pl Enablement, Having all Production and Bench Records, Carrying fwd the History information
Report for Volume and Pre-Prod Comparison | Rakesh | Sendil |  |  | Completed | A report that compares current quarters volume and Pre-Prod count as of a particular day
Marginn Tracker | Gokila | SriRam | 2019-08-20 |  | Completed | Margin Tracker report -- Practice Wise, Backend part is completed
BE TRAcker -- SS Access Change | Himanshu, Rashmin | Deepak |  |  | Stopped | Access in BE Tracker should be changed. SS Access-- A person having one account access in SS should have only that account's access and not other SS groups
Volume Gaps Report | Gokila | Deepak |  |  | Completed | To add SS access logic
PBS Alcon Gaps Summary Report | HItesh | Ravi |  |  | Completed | Added Columns, TBB, ContractCode, Service Offering
Buffer Portal Rework | Teja | Ganesh Prabhu |  |  | Completed | Reverted the changes related to TMS
Package Configurations | Hitesh | Sheethal |  |  | Completed | Changing the configurations of packges to run form VM instead of Banaglore server
Backup D Drive Bangalore Server | Rashmin | CCD |  |  | Completed | Taking back up of D Drive of Bangalore by cleaning all un necessary files
BE Tracker Call Date | Gokila | Sheethal |  |  | Completed | Made Call Date Changes Dynamic. If the Previous
BE Tracker | Gokila | Deepak | 2019-08-09 |  | Completed | Adding PKG as a new Service Line
Volume and RTBR reports | Rashmin | Deepak | 2019-08-09 |  | Completed | Adding PKG as a new Service Line
Refactoring of BUR Portal | Rahul | Sheethal |  |  | Completed | Refactored and deployed BUR Portal
Created Cube for BudgetedVsAllocated_Effort file. i.e 1st link of Volume load mail. | Rashmin | Ravi | 2019-08-20 |  | Completed | Creating cube for Budgeted Vs allocated report
Visa Dashboard | Teja | Amit Chakravarthy | 2019-08-09 |  | Completed | Few columns for FS US are changed. Accomodating those changes in the code
OEI Portals | Rashmin | Sheethal |  |  | Completed
BE Tracker | Gokila, Rashmin | Deepak | 2019-08-12 |  | Completed | BE Tracker Upload to excel functionality fixes
BE Tracker | Gokila,Rashmin | Ravi | 2019-08-12 |  | Completed | Freezing Actuals values while uploading data from the excel
Fin Pulse Upload | Rahul,Rashmin | Deepak | 2019-08-09 |  | Completed | Uploaded Finpulse, refreshed Rev Prod Expense combination cube and Rev Prod Cube
BE-RTBR and BE-Alcon gaps | Teja, Hitesh | Ravi | 2019-08-20 |  | Completed | The excel download for the BE-RTBR and BE-Alcon gaps merges two or more columns for many single columns.
Space Issues in Bangalore and Pune server | Hitesh, Sheethal | Sheethal | 2019-08-09 |  | Completed | Resolved Space issues in bangalore and Pune server by removing all temp files in users profiles
ONB USDLY Refresh | Teja | TPD | 2019-08-09 |  | Completed | ONB USDLY refreshed with latest Data shared by TPD
Missing DU Mailer List | Teja | Sheethal | 2019-08-09 |  | Completed | Changed the missing DU mailing list
Actuals Upload on BE Tracker | Gokila, Rashmin | Ravi | 2019-08-09 |  | Completed | Uploaded Jul actuals to the BE Tracker
SS BE Report Automation | Rashmin | Deepak,Ravi |  |  | Completed | Rev Volume Report automation for SS
SS BE Report Automation | Teja | Deepak,Ravi |  |  | Completed | Onsite Bench and Buffer Tab in SS BE Report automation
SS BE Report Automation | Rahul | Deepak,Ravi |  |  | Completed | BE RTBR tab in SS Be Reprot Automation
Considated Cube- BE report | Gokila | Ravi |  |  | Completed | Completed automation of Considated Cube. The consolidated report in the BE tracker is now a cube
Visa Dashboard | Teja | TPD |  |  | Completed | New Status Column has been mapped and the Visa Table loaded with the new Visa Statuses
IVS Release List | Rahul | TPD |  |  | Completed | TPD added 5 new editable columns to the release list. Going forward, we will be getting the data to be uploaded on weekly basis.
IVS Release List | Rahul | TPD |  |  | Completed | 1) Dispalying Total Number of records 2) Changing the order of filters
PBS Alcon Report Prctice wise split | Rakesh | Crystal |  |  | Completed | Splitting PBS Alcon report practice wise and uploading the same on sharepoint-- SS
ONB Tracker | Rakesh | TPD |  |  | Completed | The issue due to personal Band coming in as NOBA in ONB tracker is resolved
Master Job Created | Hitesh | Sheethal |  |  | Completed | A master job has been created which loads the data sequentially one after the other like OMS, Manpower, ATA, Volume and RTBR. IT is scheduled to run three times a day
BE Report Automation -- IHLCP, MFG | Rakesh, Rachana | Ravi,Deepak |  |  | Completed
Visa Utilization Report | Rakesh | TPD |  |  | Completed | Made Changes in the Visa Load and changed Visa Utilization Report to accommodate the new changes in the Visa Dump
OEI - FP ReScheduling | Teja, Rahul | Sudeep |  |  | Completed | To Add FP Rescheduling in OEI Individual Mailers, Self Service Portal
BE Tracker -- Adding Alerts | TBD | Delivery |  |  | Completed | Sending Alert Mailers to Account DMs when SS DMs change either Revenue or volume SS BE
Migration Issues | Rakesh, Hitesh | Sheethal |  |  | Completed | Issues Fetching UserName in BE Adminconsole and Expense Budgeting applications after deploying the code
Utlization Report Automation | Rahul, Gokila | Preksha |  |  | Completed | Utilization and Role Mix automation
Margin Tracker, Summary Page | Gokila | Sriram |  |  | Completed | A summary Page for Margin Tracker which has current and previous three quarters data
Finpulse cube | Rachana | Ravi |  |  | Completed | POC on Merging all different dimensions into a single dimension
Refactoring of Individual mailers -- Alcon | Teja | Sheethal |  |  | Completed | Refactored the code and optimized
Margin Tracker, Practice wise | Gokila | Sriram |  |  | Completed | Prctice wise cubes for marging tracker
BE Portal Home page KT and Calldate KT | Gokila | Sheethal |  |  | Completed | KT on these two toipics are given by gokila to Teja nad Rachana
Unbilled revenue certification Updates for this quarter | Teja | Anish |  |  | Completed | Unbilled certification data for the quarter loaded
PBS Alcon Report Practice wise split | Rakesh | Crystal |  |  | Completed | Splitting PBS Alcon report practice wise and uploading the same on sharepoint. Done for all practices except SS
BE Admin Console Migration | Hitesh | Sheethal |  |  | Completed | Migrated BE Adminconsole page to VM1
Expense Budgeting Migration | Hitesh | Sheethal |  |  | Completed | Migrated Expense Budgeting Syetem tp VM1
MIGration of all the files and folders in Bangalore Server | Rashmin , Sheethal | CCD |  |  | Completed | Taking a backup of all the files, Folders etc from Bangalore server to VM as Bangalore server's OS needs to be upgraded form current version 2008 to 2016
Modifications in SS BE Report | Rashmin | Deepak |  |  | Completed
IVS OPS Report Automation | Rashmin, Rakesh | Deepak |  |  | Completed | IVS OPS report is being automated. Visa tab is pending. Visa reports from corporate has issues, Hence, visa tab alone is pending
Fact_Manpower Cube | Rahul | Ravi |  |  | Completed | To add few columns in the cube, Testing in progress
IVS FS2- Utilization Mailers | Hitesh, Teja | Ajay |  |  | Completed | Sending IVS FS2 utilization mailers Emp DU Head wise on a daily basis
Month End allocation Expiry Mailers | Himanshu, Teja | Sona |  |  | Completed | Automation of the month end allocation expiry mailers
RTBR Gaps Report -- SS Wise | Rakesh, Gokila | Deepak |  |  | Completed | To add SS logic in RTBR Gaps report
IVS Utilization -- Internal Production | Teja | Srini |  |  | Completed | To add Internal Production as a column in utilization mailers
DevOps Utilization and Alcon Gaps Report automation | Teja | Deepak |  |  | Completed
Devops Utilization and Alcon Gaps Mailer Automation | Teja | Deepak |  |  | Completed
Access logic in BE tracker | Gokila | Ajay |  |  | Completed | A logic to provide all SS Lines data while the BE Report is downloaded even if the DM has only functional access
IFRS Group in Cube | Rashmin | Anish |  |  | Completed | To bring in IFRS gropu column in the rev prod expense Manpower cube
SS DM in Cube | Rashmin | Deepak |  |  | Completed | Adding SSDM column in the cube
Calculated columns in cube | Rachana | Ravi |  |  | Completed
BE Report Automation -FS US | Gokila, Teja | Ajay |  |  | Completed | Automating BE Report for the practice 'FS US'
BE Report Automation -FS Non US | Rakesh, Gokila | Ajay |  |  | Completed | Automating BE Report for the practice 'FS Non US'
Enabling SS BE alert Mailers - RCL | Gokila | Ravi |  |  | Completed | Enabled automated maielrs for BE alert Mailers for RCL
Portal For SS BE report | Rashmin | Deepak |  |  | Completed | Make it access Based
ECS BE Report Automation | Rakesh | Crystal |  |  | Completed | Automation of BE Report for ECS
SS BE Alert Maielrs for IHLCP And MFG | Rakesh | Sriram |  |  | Completed | Enabled BE Alert mailers for IHLCP and MFG practice
Assist Edge Features training | Sheethal,Hitesh, rashmin | Srini |  |  | Completed | Learning Assist Edge features for implementing it in a chatbot project
Configuring Individual Mailers in VM | Rahul | Sheethal |  |  | Completed | Configuring Individual Mailers in VM1
Addition of Onsite Offshore deputee, Practice columns in USDLY BUR | Himanshu | Ravi |  |  | Completed | Adding Onsite Recruit/Offshore Deputee, Practice fields in BUR
BE Report automation -- ECS RCL | Rakesh | Crystal |  |  | Completed | review changes by crystal
BE Report automation -- DevOps | Rachana | Deepak |  |  | Completed | DevOps BE Report automation using Macros
Moving Finpulse Cube to Pune App Server | Hitesh, Rashmin | Sheethal |  |  | Completed | Moved Finoulse database to pune App Server
BE Tracker KT | Rashmin,Gokila | Sheethal |  |  | Completed | Giving BE Tracker KT to the entire team and also preparing the documents necessary for performing certain activities
Self Service portal Testing | Rahul,Himanshu | Sheethal |  |  | Completed | Self Service portal in VM is being tested by Sudeep by sending Test Mailers
Android Studio Set Up | Hitesh,Tanvi | Anish |  |  | Completed | Few drivers are missing, that is being installed
BE Report Automation FS US, FS Non US | Gokila | Ajay |  |  | Completed | Addition of Production HC column in volume and Buffer tabs
Automation -Demand Load | Tanvi, Himanshu, Teja | Anish |  |  | Yet-To-Start | Automating Demand Load like RTBR/Volume, by directly logging in with Anishs credentials and downloading the demand files
Automation of Margin Trend And ABC Analysis | Gokila, Rahul, Teja | SriRam |  |  | Completed | Automating the process of adding the mothly actuals and refreshing the pivots of Margin trend tool and ABC Analysis file
ONB Tracker Optimization | Hitesh | Sheethal |  |  | Completed | We had refresh issues in ONB tracker, the same has been fixed by optimizing the query
Issues in Macros - Selfservice portal | Rahul, Himanshu, Rashmin | Sheethal |  |  | Completed | Macros execution issues when we are disconnected from Remote Desktop Connection
Digital Summary Report Modifications | Himanshu | Deepak |  |  | Completed
BCMS Tracker | Rashmin, Hitesh | Anish |  |  | Completed | A tracker to track the BCP due to Covid-19
Migration of Applications from Bangalore server to VM | Team | CCD |  |  | Completed | Moved all the applications to new VM
Changing Exchange rates | Rashmin, Gokila, Rakesh, Rachana | Ravi |  |  | Completed | Exchange Rates to reflect 2020 calues in all the reports
Release Tracker | Rahul, Teja | Dharma(TPD) |  |  | Completed | Bulk upload functionality to all the users
Reports Automation | Hitesh, Tanvi, Himanshu | Sheethal |  |  | Completed | A new model framework to have all the reports automation in a particular manner. Global declaration of ll the variables used throughout the automation
IVS Financials Report Automation | Rachana, Rakesh | Deepak |  |  | Completed | A monthly report -- IVS Financials Automation.
Portal to host all weekly BE Reports | Rashmin, Rakesh, Rachana | Ravi |  |  | Completed | A portal from which all the Weekly BE Reports can be automated.
Rev Momentum Report Automation | Rashmin, Gokila, Rahul | Manoj |  |  | Completed | Rev Movememnt Report automation
SOA Migration | Team | Deepak |  |  | Completed | Fixed SOA Migration related changes in all BE Reports and portals
Finpulse Manpower Cube Changes | Rachaa, Rahul | Crystal |  |  | Completed | Addition of Practice Cost Opt, SDM Cost Opt and Project Cost Opt column in the Finpulse Manpwoer cube
BPO TSO Report Automation | Gokila, Teja | Sheethal |  |  | Completed | Automation of BPO TSO Report that we send on Wednesdays
RTBR Cube Changes | Gokila | Ravi |  |  | Completed | Addition of columns DM and segreggating Month column, Seperating API Digital
RDC portal | Himanshu | Himanshu |  |  | Completed | A portal to check with whom te servers are instead of asking everyone in the team. The portal provide infromation on with whom the server is at any point in time. The person with whom the machine is can be reached out and asked to release the server.
FS2 Utilization Mailer | Himanshu | Ajay |  |  | Completed | To add utilization trend for last 10 days in FS2 utilization report mailer
BOT Extraction Portal | Rashmin | Lavanya Yadla |  |  | Completed | A portal to copydata provided by PMs into BOT Extraction Template
RTBR Cube Changes | Rahul, Tanvi | Ravi |  |  | Completed | Needs to add a column called month. Currently, each month is a separate field.
Volume Ops Automation | Tanvi, Gokila | Ajay |  |  | Completed | Volume Ops report needs to be automated. This will be refreshed everyday
Milestone Report Automation | Tanvi | Sheethal |  |  | Completed | Milestone report required for IVS Ops report has been automated
ECS ,RCL BE Report Automation | Rakesh | Crystal |  |  | Completed | Some changes in the column ordering and macro changes
Macro Help-- ECS Team | Rashmin | Srini |  |  | Completed | Helping ECS team with Macro creation
Finpulse cube Demo to CIS Team | Sheethal | CIS |  |  | Completed | Gave Finpulse cube demo to CIS Team
Adding IVS Financials Report in Dashbaord | Rachana | Deepak |  |  | Completed | Adding IVS Finanacials Report under Miscellaneous Tab in Dashboard
Adding Volume Ops Automation in IVS Dashboard | Gokila, Tanvi | Ajay |  |  | Completed | Adding FS US/NON US Volume ops report in the Dashboard
Adding BudgetedVsAllocated sheet in Dashbaord | Rashmin, Teja | Sheethal |  |  | Completed | Adding BUdgetedVsAllocated sheets that we get in amail in the Dashboard
Finpulse Load Automation | Rachana | Sheethal |  |  | Completed | Automating Finpulse Load
RTBR Report- SDM View and MC View | Himanshu | Sheethal |  |  | Completed | Logic of SS to be fixed
Status report Autonation | Teja, Tanvi | Sheethal |  |  | Completed | Status Report Automation
BE momentum | Rakesh | Manoj |  |  | Completed | Data dumps for RTBR, Volume and Revenue to be added in BE Momentum Report
SS BE Report Automation | Rashmin | Manoj |  |  | Completed | Digital Data, Practice wise Digital Data tabs to be included in SS BE Report
Report Server Procument | Sheethal | Anish |  |  | Completed | Raised a AHD Request for procuring the software, Procured a softwre in VM2, Evaluation version
History Feature in Release portal | Rahul | Dharma(TPD) |  |  | Completed | Need to maintain history between uploads. Uploads happens every Monday, Wednesday and Friday. A button to downlad History Details
Financial Reports Automation | Rahul, Rashmin, Himanshu, Rachana, Gokila | Sriram |  |  | Completed | Financial Reports Automation
Addition of ProjectDU column in BUR Report | Himanshu | Deepak |  |  | Completed | Addition of ProjectDU column in BUR Report
IVS SL leads Report Automation | Hitesh | Jayashree (TPD) |  |  | Completed | Automated Report to be sent for IVS DMs
IVS Financials Report-Modification | Rachana | Deepak |  |  | Completed | Addition of few calculated columns in IVS Financial Report
Addition of Country column in Revenu and Volume BE Reports | Rashmin | Ravi |  |  | Completed | Addition of Country column in BE Report - Revenue, Volume
IVS SL Leads Report automation | Gokila | Jayashree (TPD) |  |  | Completed | A report will be sent to all the IVS DM and DHs on US Bench details
Prepare checklist for Report server Migration | Sheethal | Arka |  |  | Completed | Preparing the checklist for SQl Reporting Server Migration
Prepare Checklist for SQL Server Migration | Sheethal | Arka |  |  | Completed | Preparing the checklist for SQl Server Migration
RTBR Cube Changes | Rachana | Ravi |  |  | Completed | Addition of new columsn like TBB, RefreshedOn, renaming parameter to Segment,Account DM field
IVS Financials | Rachana | Deepak |  |  | Completed | Addition of Monthly data
BTN Tracker | Rahul | Sona |  |  | Completed | Renaming BTN Portal and afdditiona of Fin Year filter
Suggestion on Input File Preparation | Sheethal | Lavanya Yadla |  |  | Completed | Suggestions on Macro preparation for IN Put file on Confirmation
Modifications in Digital RTBR Report | Gokila | Deepak |  |  | Completed
Automation of BOT Extraction Input file | Sheethal, Hitesh, Himanshu | Lavanya Yadla |  |  | Completed
Financial Reports Automation_Incorporating review Comments FS NON US, FS US | Rachana, Rashmin, Rahul, Gokila | Ajay |  |  | Completed
Financial Reports Automation_Incorporating review Comments Margin Tools | Rahul | Sriram |  |  | Completed
Changin Date format of a column in Release tracker | Tanvi | Dharma(TPD) |  |  | Completed
Adding Date filter in Status Report | Teja | Sheethal |  |  | Completed
Icompaz BE Tracker -Phase 1 | Rashmin | Ravi |  |  | Completed | Developed Icompaz BE tracker
Icompaz BE Tracker -Phase 2 | Rashmin, Gokila | Ravi |  |  | Completed | RTBR upload, Hom epage report and adding RTBR column in revenue download report
Macro Help-- TPD Team | Rahul, Teja | Prathima (TPD) |  |  | Completed
Release portal - Functaional Change | Rahul | Dharma(TPD) |  |  | Completed
SS BE Report- Changes | Gokila, Rashmin, Rachana | Manoj |  |  | Completed | SS BE Report Changes
BE Estimation Automation | Rachana,Gokila | Crystal |  |  | Completed
Talent Mobility Portal- Phase 1 | Tanvi, Himanshu | Amit Chakravarthy(TPD) |  |  | Completed
Talent Mobility Portal- Phase 2 | Tanvi | Amit Chakravarthy(TPD) |  |  | Completed | Instead of daily refresh, TPD team will provide monthly data for uplaod.
Digital Audit Mailers | Himanshu | Preksha |  |  | Completed
Research on Open source Reporting tools | Sheethal, Rashmin | Anish |  |  | On-Hold | C# code has replaced SSIS. Birt, we are unable to proceed. Trying to convert SQL to postgres
Request to get Reporting Server Standard Edition in VM2 | Sheethal | Anish/Srini |  |  | Completed | Got Evaluation Version in VM2
Freshers Hiring for Rotation | Sheethal | Srini |  |  | Completed
ECS RCL- BE Weekly report Changes | Teja | Crystal |  |  | Completed | New filter Geo, CSG to be added in all the tabs in the report DU Mapping to be updated in all the tabs Next quarter BE should start appearing when we are in 8th day , 2nd month of current quarter
Research on Migration from SQL Server to Postgres | Hitesh | Sheethal |  |  | Completed | Installed Postgres, Migrating Expense DB
POC on Demand load without SSIS package | Himanshu | Sheethal |  |  | Completed | Have implemented Manpower, OMS, Demand load and EMP Load
Volume Ops report automated Mailer | Teja, Tanvi | Ajay |  |  | Completed | Automated mailer for volume ops daily mailer
VM for POCs | Sheethal | Sheethal |  |  | Completed | Procured a 100 GB VM for POC
KT on Cube for CIS team | Sheethal | CIS team |  |  | Completed
SS BE Report Modifictaion | Rashmin | MAnoj |  |  | Completed | Modifictaions in SS BE report
Finpulse automation- Margin Sheet to be changed | Rahul | Sriram |  |  | Completed
AR>180 days automation | Tanvi, Himanshu | Manoj |  |  | Completed | A self service portal to upload AR > 180 days file and generate automated files
Adjusted RTBR Automation | Rashmin, Gokila, Rachana | Crystal |  |  | Completed
Adding Adjusted RTBR in RTBR Momentum report | Rahul | Manoj |  |  | Completed
BE Estimation Automation -- Allowing users to edit the estimated values | Rachana, Gokila | Crysta, Ravi |  |  | Completed | BE Stimation Automation -- Allowing users to Edit the values that get populated based on the formulae
C# code to do Volume load | Teja | Sheethal |  |  | Completed
c# Code to do RTBR Load | Teja | Sheethal |  |  | Completed
SS BE Report -- Practice Filter addition | Rashmin | Manoj |  |  | Completed | Adding a filter for Practice in SS BE Report
Icomaz BE Tracker KT | Tanvi, Teja | Sheethal |  |  | Completed | KT ON Icompaz BE Tracker
Refactoring Utilization Report | Rahul | Sheethal |  |  | Completed | It was a cube earlier, made it a macro
Self service portal Package conversion to C# | Team | Sheethal |  |  | Completed
Additional Scenarios Portal | Tanvi | Preksha |  |  | Completed
Open to Market Place Reports | Himanshu | Amit (TPD) |  |  | Completed
KT To New Joinees | Team | Sheethal |  |  | Completed
Enhancements in Revenue Momentum Report | Teja, Gokila | Manoj |  |  | Completed | Adding next quarter's data on the 8th day of 2nd month of current quarter
Refactoring Devops weekly BE Report | Rachana | Sheethal |  |  | Completed
Switching over to Active server in case of server breakdown | Sheethal | Anish |  |  | On-Hold | Have raised CCD request for thei help on this. CCD says tis is not possible in case of a VM
CSG BE Tracker report | Rashmin | Sona |  |  | Completed | Adding Master Customer Unit to the CSG BE report--
FS US -- Demannd Mapped Demand and Future Allocation View-- Tracker | Devika, Gagan, Gokila | Ajay |  |  | Completed
FS US -- Demannd Mapped Demand and Future Allocation View-- Report | Saneesh, Nikita, Gokila | Ajay |  |  | Completed
FS US -- Demannd Mapped Demand and Future Allocation View-- Self Service Portal | Dhanush, Sharmila, Gokila | Ajay |  |  | Completed
FA-US, Non US-- Volume Ops automation reprot | Teja | Ajay |  |  | Completed | To include, Critical Demand, Mapped Demand, Production head count Etc..
Digit BE tracker | Teja, Gagan | Deepak |  |  | Completed | A digital BE Tracker to tracker Digital numbers
Extractio BOT Automation-- CAREMARK account | Himanshu | Lavanya Yadla |  |  | Completed
Cube creation to include GDLY, IPSIVS, Manpower report production data | Gagan, Sharmila, Gokila | Ravi |  |  | Completed | HC Cube
VLDN Tracker | Saneesh, Rachana, Sharmila, Dhanush | VLDN Team |  |  | Completed | Migrating VBA based code to C#
POC of sharepoitn page to VLDN Team | Teja, Nikita | VLDN Team |  |  | Completed | POC on replicating the links on sharepoint portal in ASP.Net
Changes in SS Lines (New BE tracker) in all downstream Reports | Gagan, Devika | Deepak |  |  | Completed | PKG Digital/Non Digital, SAP Digital/Non Digital/, clud/Infra columns addition in the BE Down stream reports
CSG BE Tracker changes | Gokila | Sona |  |  | Completed | Modifications --to Include Menu option for Users , Mapped More master customers for users
Self Service portal for Adding/Updating MC for CSG Users | TBD | Sheethal |  |  | Yet-To-Start
Rate Analysis Automation | Gagan, Gokila | Sriram |  |  | Completed
Modifications to SS BE Report | TBD | Manoj |  |  | Yet-To-Start
Volume Ops Automation Mailer-- IHLCP, MFG | Devika | Sriram |  |  | Completed
FS US, NON US Weekly BE Report modifications | Nikita | Ajay |  |  | Completed
Utilities page VLDN Tracker | Sharmila | VLDN Team |  |  | Completed
Nomination Portal -- Adding Score Card | Gagan, Sharmila | Debasis, Shalini |  |  | In-Progress | Adding Score Card to Nomination Portal.
VLDN Tracker-- Vikramah Changes 1.2 | Saneesh, Elakkiya | Lata, Sunil |  |  | In-Progress | Additional requires for Version 1.2
VLDN Tracker -- CRM Changes | Saneesh, Elakkiya | Lata, Sunil |  |  | In-Progress | Toinclude CRM data for a combined view
POC On Power BI Reports | Devika | Sheethal |  |  | In-Progress | To have Power BI reports for certain BE parameters
Fin Analysis Checklist Document | Sharmila, Lavanya, Vinothini, Nishu | Sheethal |  |  | In-Progress | A checklist to ensure all parameters in Fin Analysis Report refresh are taken care of
FTE Macro | Dhanush, Devika | Jawahar |  |  | In-Progress | A macro to have FTE Validation scenarios
RAR Report | Elakkiya | Ajay |  |  | In-Progress | RAR report changes
Estimation of Implementation plan-- CRM VLDN | Sheethal | Sunil |  |  | In-Progress | To comeup with a rough estimationof the time taken to complete the tasks involved in CRM implemntation
SMTP Configuratuion in VM1 | Sheethal | Sheethal |  |  | In-Progress | To get the new IP Mapped to SMTP Server, so that mailers get triggered from VM1
POC on Gateway | Sheethal | Sunil |  |  | In-Progress | To check and get Gateway installed so that POwerBI can connect to the SQL Server and to publish reports

## Sheet2
ApplicationName | Assignee | ApplicationOwner | ETA | ActualCompletion | Status | Remarks | Instructions :
Consolidated BE Reprot | Gokila | Sheethal | 13/2/2018 |  | Completed | Refactoring the code for consolidated BE Report